## MS SIP Evaluation_17-18
Initiative #1 Evaluation
Initiative #1 Description:
Goal Area:
Performance Objective:
Initiative #1:
What was the need being addressed by this initiative?
What was the reason for selecting this initiative?
What were the intended results of this initiative?
Initiative #1 Implementation Evaluation
Describe the steps followed to implement this initiative. Include persons responsible and timeframe for the implementation.
What evidence is available to show this initiative was fully implemented?
Were there any barriers to implementing this intiative? Why or why not?
Were there any barriers to maintaining this initiative through the expected timeframe? Why or why not?
Were appropriate resources provided to all stakeholders to implement and maintain this initiative? Why or why not?
Are changes needed to improve the full implementation of this initiative? What changes?
Initiative #1 Effectiveness Evaluation
What data were collected to monitor and evaluate the effectiveness of this initiative?
Are there enough accurate data points to evaluate the effectiveness of this initiative?
Citing specific data points, was the initiative successful in addressing the need? Why or why not?
Is it possible that other initiatives affected the need more than the intended initiative? Why or why not?
Were there any unintended consequences from this initiative (positive or negative)?
Will you continue with this initiative in the next school year? If so, what changes need to be made to improve its effectiveness?
Initiative #2 Evaluation
Initiative #2 Description:
Goal Area:
Performance Objective:
Initiative #2:
What was the need being addressed by this initiative?
What was the reason for selecting this initiative?
What were the intended results of this initiative?
Initiative #2 Implementation Evaluation
Describe the steps followed to implement this initiative. Include persons responsible and timeframe for the implementation.
What evidence is available to show this initiative was fully implemented?
Were there any barriers to implementing this intiative? Why or why not?
Were there any barriers to maintaining this initiative through the expected timeframe? Why or why not?
Were appropriate resources provided to all stakeholders to implement and maintain this initiative? Why or why not?
Are changes needed to improve the full implementation of this initiative? What changes?
Initiative #2 Effectiveness Evaluation
What data were collected to monitor and evaluate the effectiveness of this initiative?
Are there enough accurate data points to evaluate the effectiveness of this initiative?
Citing specific data points, was the initiative successful in addressing the need? Why or why not?
Is it possible that other initiatives affected the need more than the intended initiative? Why or why not?
Were there any unintended consequences from this initiative (positive or negative)?
Will you continue with this initiative in the next school year? If so, what changes need to be made to improve its effectiveness?
Initiative #3 Evaluation
Initiative #3 Description:
Goal Area:
Performance Objective:
Initiative #3:
What was the need being addressed by this initiative?
What was the reason for selecting this initiative?
What were the intended results of this initiative?
Initiative #3 Implementation Evaluation
Describe the steps followed to implement this initiative. Include persons responsible and timeframe for the implementation.
What evidence is available to show this initiative was fully implemented?
Were there any barriers to implementing this intiative? Why or why not?
Were there any barriers to maintaining this initiative through the expected timeframe? Why or why not?
Were appropriate resources provided to all stakeholders to implement and maintain this initiative? Why or why not?
Are changes needed to improve the full implementation of this initiative? What changes?
Initiative #3 Effectiveness Evaluation
What data were collected to monitor and evaluate the effectiveness of this initiative?
Are there enough accurate data points to evaluate the effectiveness of this initiative?
Citing specific data points, was the initiative successful in addressing the need? Why or why not?
Is it possible that other initiatives affected the need more than the intended initiative? Why or why not?
Were there any unintended consequences from this initiative (positive or negative)?
Will you continue with this initiative in the next school year? If so, what changes need to be made to improve its effectiveness?

## MS Needs Assessment_18-19
CCRPI | 2014-2015 | 2015-2016 | 2016-2017 | 3-yr Avg | Data Sources
CCRPI Score - School | 62.4 | 54.1 | 56.9 | 57.8 | GADOE portal
CCRPI Score - District | 62.4 | 57.9 | 63.1 | 61.1333
CCRPI Score - State | 75.5 | 73.6 | 72.9 | 74
Georgia Milestones | 2015-2016 | 2016-2017 | 2017-2018 | 3-yr Avg | Data Source
% Developing Learner or Above - ELA | 59 | 57 | 58 | 58 | SLDS
% Developing Learner or Above - Math | 62 | 55 | 55 | 57.3333
% Developing Learner or Above - Science | 45 | 27 | 16 | 29.3333
% Developing Learner or Above - Social Studies | 47 | 50 | 55 | 50.6667
% Proficient or Distinguished Learner - ELA | 0.6 | 15% Prof | 21 | 10.8
% Proficient or Distinguished Learner - Math | 1 | 1 | 15 | 5.6667
% Proficient or Distinguished Learner - Science | 0.6 | 4% Prof | 1 | 0.8
% Proficient or Distinguished Learner - Social Studies | 2 | 6 | 8 | 5.3333
iReady | EOY 2016 | EOY 2017 | EOY 2018 | 3-yr Avg | Data Source
% Students Reading on Grade Level - 6th Grade | 14 | 9 | 10 | 11 | iReady->Reports
% Students Reading on Grade Level - 7th Grade | 11 | 10 | 15 | 12
% Students Reading on Grade Level - 8th Grade | 20 | 16 | 18 | 18
On Grade Level Lexile (%) | 26 | 30 | 28 | 28 | iReady->Reports
% Students Math on Grade Level - 6th Grade | 33 | 40 | 28 | 33.6667 | iReady->Reports
% Students Math on Grade Level - 7th Grade | 8 | 18 | 38 | 21.3333
% Students Math on Grade Level - 8th Grade | 40 | 40 | 25 | 35
On Grade Level Quantile (%) | 28 | 32 | 29 | 29.6667 | iReady->Reports
Reflection Questions: How are student Lexiles used instructionally to improve student growth? How are Lexiles communicated to parents to ensure they understand what these scores mean? How are Lexiles communicated to students and used for goal setting? What training do teachers receive to enhance their professional knowledge about Lexiles? Does your professional learning for Lexile instruction include all content teachers? How can Media Specialist support increased Lexile measures?
1. Student Lexile scores are used by teachers to plan instruction with flexible groups. 2. Lexile scores are communicated to parent by sending reports via progress reports and report cards. Additionally during parent conferences and parent information nights teachers, counselors and media specialist take time to share with parents how to understand the report and design a plan to help their child improve. 3. Teacher need extensive training with iReady. Often times they know just how to adminster the assessment and view results, but what is lacking is what to do with the data and how to ensure that this data is used to move student growth. 4. Training for teachers would include all teachers because our literacy gap is a schoolwide problem, and one we will work together to solve. 5. The media specialist is an integral part of our school wide literacy plan. She works with teachers to create lessons and find appropriate resources. WIth students, the media specialist works with them to assist them in finding books in their lexile range.
Reflection Questions: How are student Quantiles used instructionally to improve student growth? How are Quantiles communicated to parents to ensure they understand what these scores mean? How are Quantiles communicated to students and used for goal setting? What training do teachers receive to enhance their professional knowledge about Quantiles. Does your professional learning for Quantiles include all content areas?
1. Quantiles are used by teachers to plan instruction with flexible groups. The goal is to see students Quantiles improve. Instruction is administered and progress monitoring is employed to monitor growth. 2. Quantiles are communicated to parents via progress reports and reports cards. Additionally, quantiles are shared with parents through conferences and parent information nights. Teachers, counselors, and the media specialist work together to plan presentations and informational sessions to ensure that parents are aware of their child progress and how we can work together to improve the math achievement. 3. Teachers need extensive training in iReady with regards to setting student goals, monitoring student progress, and using the data from universal testing to drive instruction. Often times, teachers pull the data from testing, but they are at a loss about what to do next. Teachers also need to be better informed about the lessons inside of iReady. 4. Professional learning for Quantiles will include all content areas.
Student Profile | 2015-2016 | 2016-2017 | 2017-2018 | 3-yr Avg | Data Source
Total Student Enrollment | 481 | 438 | 400 | 439.6667 | Infinite Campus (Student Information->Reports->Enrollment Summary
Students Absent 6+ Days (%) |  | 66 | 74 | 70 | Infinite Campus (RCSS Custom Reports->Attendance->Attendance by Min Nbr of Days
Discipline Incidences | 918 | 775 | 950 | 881 | Infinite Campus->Behavior->Reports->Incident. Click on List by Year to see other school years.
Reflection Questions: What is your schools attendance plan? How do you address attendance issues? Phone call? Notes home? Home visit? Do you use your parent facilitator or designee? Who monitors attendance and how it affects your CCRPI score? Are there any rewards systems in place for attendance? Are these rewards monthly? Quarterly? Yearly?
1. Our school attendace plan includes mutliple interventions. For the students with established attendance patterns, parents have been contacted with a mailed letter outling the importance of daily school attendance as well as the interventions that will be in place for these students. Each nine weeks the school will celebrate attendance improved attendance. Each nine weeks there will be also be a celebration for student with perfect attendance. The attendance plan includes teachers call the parents the first absence. The school has set Shout Point to contact the parents to report daily absences. 2. Parent contact is made after the first absences. 3. The school tracks attendance through Infinite Campus with the teachers entering the HR attendance by 10:00 AM each day. The school tracks attendance weekly with the Attendance Committee. 4. All teachers take attendance at the beginning of each class. Teams of teachers meet together to review the attendance data to check for discrepancies. 5. Attendance issues are handled by the Attendance committee following the district attendance protocol with phone calls, conference, and letters sent home. When necessary, the committee includes the support of the school social worker. The leadership team in conjunction with the attendance committee monitors how attendance is impacting the school's CCRPI score
Faculty & Staff Profile (2015-2016) | 1 to 3 Years | 4-10 Years | 11-20 Years | 21+ Years | Data Source
Current Principal's # of Years in Position | <1 |  |  |  | School-level Data
Teaching Staff # of Years in Current School | 8 |  |  |  | School-level Data
Teaching Staff # of Years in Profession | 7 | 1 | 4 | 5 | School-level Data
| 2014-2015 | 2015-2016 | 2016-2017 | 3-yr Avg | Data Source
% Administrator Absent 6+ Days |  |  |  |  | School-level Data
% Teachers Absent 6+ Days |  |  |  |  | School-level Data
% Staff Absent 6+ Days |  |  |  |  | School-level Data
Reflection Questions: Do you monitor teacher/staff attendance? Are any teachers/staff chronically absent? Do these teachers/staff miss Mondays and Fridays more so than others?
Yes, the school monitors teacher/staff attendance monthly. There were no noticeable increases on Monday and/or Fridays
All numbers listed below are percentages.
TKES Standards (%) (2016-2017) | Level I | Level II | Level III | Level IV | Data Source
1. Professional Knowledge | 0 | 4 | 72 | 24 | School-level Data
2. Instructional Planning | 0 | 4 | 80 | 16 | School-level Data
3. Instructional Strategies | 0 | 4 | 80 | 16 | School-level Data
4. Differentiated Instruction | 0 | 12 | 80 | 8 | School-level Data
5. Assessment Strategies | 0 | 4 | 92 | 4 | School-level Data
6. Assessment Uses | 0 | 8 | 92 | 0 | School-level Data
7. Positive Learning Environment | 4 | 12 | 48 | 36 | School-level Data
8. Academically Challenging Environment | 4 | 16 | 76 | 20 | School-level Data
9. Professionalism | 0 | 4 | 76 | 20 | School-level Data
10. Communication | 0 | 4 | 80 | 16 | School-level Data
School Culture Data Profile | 2014-2015 | 2015-2016 | 2016-2017 | 3-yr Avg | Data Source
Student Mobility (%) | 17.8 | 22 | 23.7 | 21.1667 | Governor's Office of Student Achievement. http://gosa.georgia.gov/downloadable-data
In-School Suspension (%) | 34 | 45 | 40 | 39.6667 | Infinite Campus->Behavior->Reports->Resolution. Click on Detail in Report Type.
Out of School Suspension (%) | 17 | 18 | 15 | 16.6667 | Infinite Campus->Behavior->Reports->Resolution. Click on Detail in Report Type.
# of Tribunal Hearings |  |  | 30 | 30
Question from the Georgia Student Health Survey with the lowest rating (Highest percentage of Strongly Disagree/Disagree or Sometimes/Never) | 66 | 62 | 66 | N/A | http://www.gadoe.org/Curriculum-Instruction-and-Assessment/Curriculum-and-Instruction/GSHS-II/Pages/GSHS-Results.aspx
Question from the Georgia Student Health Survey with the highest rating (Highest percentage of Strongly Agree/Agree or Always/Often) | 97 | 97 | 95 | N/A | http://www.gadoe.org/Curriculum-Instruction-and-Assessment/Curriculum-and-Instruction/GSHS-II/Pages/GSHS-Results.aspx
Reflection Questions: How do out-of-school suspensions affect attendance? Do you have interventions in place that could replace suspensions as a form of punishment? What positive behavior reinforcement program or initiatives does your school have in place?
Out of School Suspension negatively impacts student attendance. In order to reduce the number of out of school suspension, the school attlempts to use in-school suspension more often. The school has created a school-wide discipline using PBIS which clearly outlines behaviorial expectations with a rewards system. The discipline committee meets monthly to review the progress and decide on next steps in order to improve behavior and ensure that stuents are rewarded for good and improved behavior.
Reflection Questions: What is your school-wide discipline plan? Does the school wide discipline plan mirror board policy? What additional policy and procedures does your school have that are unique? Is your faculty and staff consistent with the school wide discipline plan? Are there any teachers that stand out that have had historical issues with discipline referrals? How is that teacher supported?
The school-wide discipline plan mirros the board policy as outlines in the district Code of Conduct. Some of the additional policies and procedures the school employs are time outs in lieu of in-school suspension and weekly "No Referral" rewards with the distribution of Rebel Bucks that can be redeemed in the Rebel Store during specified times. The entire school is working to be consistent with the school-wide plan, and the fact that the team with representation from each grade level authored the plan made this possible. There are no teachers with historical discipline issues.
Reflection Questions: What types of training have you offered to address student discipline? What types of training is needed to address student discipline? For students who are long term (5-10 day suspension/ alternative) suspended, how are they transitioned back in the school? How are you monitoring and supporting academics of the students who are chronically suspended?
Reflection Questions: What areas of concern are revealed in the Georgia Student Health Survey results? How does this relate to your School Climate Star Rating? How are these concerns addressed in your day-to-day operations? Do they represent gaps in your procedures or follow-through on your procedures? What needs to change to improve on these concerns?
#31 Students in my school take pride in keeping our school building in good condition. #46 My parents, or other adults at my house, think that education is important.
Reflection Questions: Do the Georgia Student Health Survey results reveal any concerns with alcohol/drug abuse or self-harm? How are these concerns being addressed? What needs to change to improve on these concerns?
Family and Community Engagement Data Profile | 2015-2016 | 2016-2017 | 2017-2018 | 3-yr Avg | Data Source
External Business/Community Partnerships (#) |  |  |  |  | School-level Data
Community Events (#) |  |  |  |  | School-level Data
School Events (#) |  |  |  |  | School-level Data
Parent Training Workshops (#) |  |  |  |  | School-level Data
Curriculum Nights (#) |  |  |  |  | School-level Data
Based on your data and the reflective questions, what are the three main initiatives that your school needs to focus on this school year?
1. Increased acheivement in all content areas. Increased Lexile Levels
2. Decreasing student dicipline referrals through building positive relationships and rewarding positive behaviors.
3. Improve student attendance.

## MS SIP Performance Measures
School: | Hephzibah Middle School
Principal: | Mr. Chris Neal
Date: | 2018-08-08
Performance Measure (with unit of measure) |  | Baseline | Target Year 1 | Actuals Year 1 | Target Year 2 | Actual Year 2 | Target Year 3 | Actuals Year 3
|  | (2015-2016) | (2016-2017) | (2016-2017) | (2017-2018) | (2017-2018) | (2018-2019) | (2018-2019)
Increase the percentage of students scoring Proficient or above on the Georgia Milestones ELA EOG |  | 20.9 | 37.44 | 15.4 | 43.85 | 21 | 58.7
Increase the percentage of students scoring Proficient or above on the Georgia Milestones Math EOG and EOC |  | 15.7G | 40.17 | 11.2 | 45.42 | 15 | 56.03
Increase the percentage of students scoring Proficient or above on the Grade 8 Science EOG and EOC |  | 18.5 | 28.68 | 3.5 | 32.3 | 1 | 28.12
Increase the percentage of students scoring Proficient or above on the Grade 8 Social Studies EOG |  | 11 | 26.26 | 5.8 | 29.9 | 8.1 | 51.2
Increase the CCRPI Score to Meet or Exceed the school's SWSS CCRPI Target |  | 56.9 | 59.7 | 56.9 | 62.7 | 57 | 65.9
Principal's Signature: |  |  | School Council President's Signature:
Leadership Team Member Signature: |  |  | Leadership Team Member Signature:

## MS SIP Initiative 1
Goal Area (Aligned to RCSS Strategy Map): |  | High Academic Acheicement for All Students
Performance Objective (Aligned to RCSS Strategy Map): |  | Increase student performance at or above grade level
Initiative 1: |  | Student lexile and quantile level will show a 3% increase by the end of 2018-2019 as measured by Spring iReady (Quantile) and the Georgia Milestone Assessment (Lexile).
Group Affected by Initiative | Research-Based Action Steps |  | Team/Leader Overseeing the Initiative | Evidence/Data the Team/Leader will collect | Specific Timeline for Implementation | Funding Source, Materials/Resources Needed
, | Provide explicit and systematic instruction in literacy. |  | Roberson, Ledwig, Rogers, Clanton, Byrd | Lesson plans & observation notes | August, 2018 - May, 2019 | General, IB, Title I - resources
| Create IB MYP units of instruction that are rich in literacy |  | Byrd | Lesson plans & observation notes | August, 2018 - May, 2019 | IB; ManageBac, IB MYP Workshops and Professional Learning
| Maximize use of web-based APPS to increase literacy (iReady, USA Test Prep) |  | Clanton | Lesson plans & observation notes | August, 2018 - May, 2019 | General, IB, Title I - online applications
| Conduct progress monitoring consistently and review and adjust instruction. |  | Clanton, McCladdie, Adriano, Ledwig | Lesson plans & observation notes | August, 2018 - May, 2019 | General, IB, Title I: folders, paper, highlighters
| Collaborate in grade level and vertical teams to review instructional strategies and student work samples. |  | ELA - Byrd; Math - Clanton; Science - Smith;SS - Neal | Collaboration minutes | August, 2018 - May, 2019 | General, IB, Title I:folders, pens, paper, highlighters, copies, binders.

## MS SIP Initiative 2
Goal Area (Aligned to RCSS Strategy Map): |  | High Academic Achievement for All Students
Performance Objective (Aligned to RCSS Strategy Map): |  | Increase student performance at or above grade level; College and career workforce readiness
Initiative 2: |  | The percentage of students present 95% of the time will increase by 3% by the end FY19 as measured by Infinite Campus attendance reports (SLDS).
Group Affected by Initiative | Research-Based Action Steps |  | Team/Leader Overseeing the Initiative | Evidence/Data the Team/Leader will collect | Specific Timeline for Implementation | Funding Source, Materials/Resources Needed
| Due to new staff, train and monitor new teachers to accurate and up\-to date with attendance records |  | Smith, Wright | Attendance Reports in Infinite Campus | August, 2018 - May, 2019 | No funds needed
| HR teachers make daily phone calls for students who are absent |  | Adriano, Ledwig, McCladdie | Contact Logs in Infinite Campus | August, 2018 - May, 2019 | No funds needed
| Monitor attendance weekly and make referrals each week; share with attendance data team |  | Ingram | Referrals to Counselors | August, 2018 - May, 2019 | No funds needed
| Offer 9 week incentives for all students with regular attendance |  | Ingram; Williams, L. | Roster of participants; photographs | August, 2018 - May, 2019 | PTO/Donations
| Implement and monitor Teacher As Advisors |  | Ingram; Neal | Lessons, perception feedback | September 2018 - May, 2019 | No funds needed

## MS SIP Initiative 3
Goal Area (Aligned to RCSS Strategy Map): |  | High Academic Achievement for All Students
Performance Objective (Aligned to RCSS Strategy Map): |  | Increase student performance at or above grade level; College and Career Workforce Readiness
Initiative 3: |  | The percentage of students receiving out-of-school suspension and in-school suspension in FY19 will see a 10% reduction when compared to FY18.
Group Affected by Initiative | Research-Based Action Steps |  | Team/Leader Overseeing the Initiative | Evidence/Data the Team/Leader will collect | Specific Timeline for Implementation | Funding Source, Materials/Resources Needed
| Reinforce Leaner Profile Attributes of the International Baccalaureate MYP across all area of the school |  | Byrd | Lesson plans, Observation data | August, 2018 - May, 2019 | IB Budget; IB Learner Attribute Poster; Flyers
| Development and Implementation of a Classroom/Grade Level Behavior matrix; expectation in hall, lunchroom, bus, transitions, theater, gym. |  | Smith | HMS Discipline Data Team minutes and recommendations. Completed Matrix | August, 2018 - May, 2019 | General Fund/Title I: Posters
| Development and Implementation of positive rewards for positive behaviors throughout the school |  | Jones, Ray | Monthy Discipline Referral Data; reports of students that receive rewards | August, 2018 - May, 2019 | PTO & Donations

## MS Professional Learning Plan
Professional Learning Plan to Support School Improvement
Supporting Initiative # | Professional Learning Strategy | Specific Professional Learning Timeline | Estimated Cost, Funding Source, and/or Resources | Person(s)/Position Responsible | Monitoring Teacher Implementation of Professional Learning | Evidence/Data of Impact on Student Learning
1 | Provide additional PL and support for implementation of IB MYP with authorization in April of 2019 | August, 2018 - May, 2019 | 12000; General, IB, Title I; ManageBac, IB MYP Workshops, Stipends, books, supplies | Adminstration, IB Coordinator | Lesson plans, observations | Evidence: Sign-In sheets, Agendas, Classroom Observations, Feedback Impact: Student's performance will increase with focus on creating engaging and relevant IB MYP units of instruction.
2 | Engage faculty in ongoing professional learning on how to engage parents and share the benefits of regular attendance | August, 2018 - May, 2019 | $3000.00; General, Title I; workshops, conferences, books, suplies | Aministration,, counselor, Leadership team | Observations from teacher conferences, meetings with parents | Evidence: Sign-In sheets, Agendas, Classroom Observations, Feedback Impact: With regular attendance, student performance/achievment will increase with iReady, as well as Georgia Milestone EOG and EOC.
3 | Create and establish a positive climate and culture in the school and classroom. | August, 2018 - May, 2019 | 2500 | Aministration,, counselor, Leadership team | Observation and focus walk notes | Evidence: Sign-in sheets, agendas, observations, feedback from perception surveys; Impact: By developing positive relationships, student's performance will increase. Student's engagment and motivation will increase.

## MS Monitoring Plan
Note: This Monitoring Plan is available for schools that do not already have a plan in use. If there is a robust Monitoring Plan in place, please submit it with your SIP.
School Improvement Monitoring Plan
Supporting Initiative # | Action Step from SIP | Specific Timeline for Implementation from SIP | Completed? Y/N | Date Completed | Evidence/Data Collected

## Title I Cover Sheet
NAME OF SCHOOL/PRINCIPAL:
NAME OF DISTRICT/SUPERINTENDENT: |  | Richmond County, Dr. Angela Pringle
DIVISION OF SCHOOL AND DISTRICT EFFECTIVENESS
Advancing Leadership çTransforming Schools
All required components of the Title I Schoolwide and Targeted Assistance are included in this template.
SIGNATURES:
Superintendent: |  |  | Date:
Principal Supervisor: |  |  | Date:
Principal: |  |  | Date:
Title 1 Director: |  |  | Date:
(Title 1 Schools only)
Title I only
The Letter of Intent for Title I Schoolwide was submitted on
Please indicate the programs that are consolidated in this plan:
School Designated as a Priority School |  | (Yes or No)
School Designated as a Focus School |  | (Yes or No)
School Name:
Date:
Planning Committee Members
Name | Position/Role | Signature
Principal
Assistant Principal
Teacher
Teacher
Teacher
Teacher
Teacher
Teacher
Teacher
Family Facilitator
Teacher
Parent
Parent
Parent
Student (9th-10th Representative)
Student (11th-12th Representative)
Note** All parents are invited and more students are encouraged to participate in the schoolwide planning process.
Comprehensive Support School
Targeted Support School
Schoolwide Title 1 School
Targeted Assistance Title 1 School
Non-Title 1 School
Opportunity School

## Title I Narrative
1. Schoolwide Reform Strategies that: Sec. 1114(b)(7)(A)(i-iii)
a. The school will be implementing to address school needs, including a
description of how such strategies will
i. Provide opportunities for all children, including each of the subgroups of students
(economically disadvantage students, students from major racial and ethnic groups,
children with disabilities and English learners [Sec 1111©(2)]) to meet the
challenging State academic standards;
Economically Disadvantage:
Foster and Homeless:
ESOL:
Migrant:
Race/Ethnicity/Minority:
Students with Disabilities:
ii. Use methods and instructional strategies that strengthen the academic program in the
school, increase the amount and quality of learning time, and help provide an
enriched and accelerated curriculum, which may include programs, activities, and
courses necessary to provide a well-rounded education;
iii. Address the needs of all children in the school, but particularly the needs of those at
risk of not meeting the challenging State academic standards, through activities
which may include --
a. counseling, school-based mental health programs, specialized instructional
support services, mentoring services, and other strategies to improve students'
skills outside the academic subject areas;
b. Preparation for and awareness of opportunities for postsecondary education
and the workforce, which may include career and technical education programs and
broadening secondary school students' access to coursework to earn postsecondary
credit while still in high school (such as Advanced Placement, International
Baccalaureate, dual or concurrent enrollment, or early college high schools);
e. (Elementary ONLY) strategies for assisting preschool children in the transition
from early childhood education.
(Middle and High School ONLY) If a middle or high school, describe how the
school will implement strategies to facilitate effective transitions for students
from middle grades to high school and from high school to postsecondary
education including, if applicable -- i. Through coordination with institutions
of higher education, employers, and other local partners; and ii. Through increased
student access to early college high school or dual or concurrent enrollment
opportunities, or career counseling to identify student interests and
skills. Sec. 1112(b)(10).
2. ESSA Requirements to include in your Schoolwide Plan
a. Define how your interventions are evidence-based; or other effective strategies to
improve student achievement. Sec. 1111(d)(B).
See Software Logic Model
See Instructional Coach Logic Model
See Title I Tutoring Program Logic Model
See Title I Class Size Reduction Logic Model
See Title I Supplemental Teacher Logic Model
See Title I Paraprofessional Logic Model
See Behavior Logic Model
See Building Parent Capacity Logic Model
See Building Staff Capacity Logic Model
b. Describe how the school will use and implement effective parent and family engagement
strategies under Section 1116, Sec. 1112(b)(7), and Sec. 1112(e)(3)(C) for parents of
English Learners.